## Sheet1
Project |  | Jefferson Murrieta Bldg 7C
Project Number |  | 60-22341 | Date | 2025-12-16
Scope | Reference # | Item | Status | Notes | Drawing set reviewed: | T:\Projects\60-22341-ADC-Jefferson Murrieta Parcel A\10_Energy Model\1. Plans & Docs\3. CD Plans\2024-07-23 2nd City Submittal
General | 1G | Confirm the PRF has the correct verification, acceptance, and installation forms listed | Checked (with comments) | Updated
| 2G | Save AHRICertificates to the project folder (project...EM\Development\EM ConstDocs & Specs) | Unchecked
3G
Architectural | 1A | Check total building area is within 5% of the arch plans | Checked (no comments)
| 2A | Check dwelling unit area is within 5% of the unit matrix total (net, not gross) | Checked (no comments)
| 3A | Confirm units counts / types align with arch unit matrix | Checked (no comments)
| 4A | Check model R-values match what is in the MVP Tracker / arch plans (roof, walls, exterior floor, slab on grade if applicable) | Checked (no comments)
| 5A | Check roof SRI and TE values match MVP Tracker / plans or specs | Checked (no comments)
| 6A | Check window values (U-value, SHGC, VT) match MVP Tracker / plans | Checked (no comments)
| 7A | Confirm windows are assigned correctly (storefront where needed, residential where needed, etc.) | N/A
| 8A | Confirm correct walls / roofs / floors framing material is asigned (concrete, metal, or wood where designed based on arch drawings) | Checked (no comments)
| 9A | Spot check a few rooms to confirm window areas, wall directions, wall areas, floors, etc. are input correctly | Checked (no comments)
| 10A | Confirm SARA inputs are input based on SARA calcs | N/A
| 11A | Confirm the "PV limited by SARA" box is only checked if that is actually the case. | Checked (with comments) | Modeled PV value is a good bit higher than the prescriptive requirement
| 12A | Confirm that only applicable exceptions to PV / Battery are being claimed | N/A
| 13A | Confirm any retail or other commercial spaces are modeled as "non-residential" and not "residential other" | N/A
14A
15A
Mechanical | 1M | Confirm mechanical system types match Mech plans | Checked (no comments)
| 2M | Confirm Mechanical system inputs (efficiencies, capacities, etc) | Checked (with comments) | Updated
| 3M | Confirm IAQ ventilation strategy and inputs (CFM, fan power) | Checked (with comments) | Updated
| 4M | Confirm ventilation rates from the mechanical designer are calculated correctly | Checked (no comments)
| 5M | Confirm the correct Acceptance testing requirements are selected for each system | Checked (with comments) | Updated
| 6M | Confirm system are assigned to the correct units/spaces | Checked (no comments)
| 7M | Confirm duct location and type | Checked (no comments)
8M
9M
Plumbing | 1P | Confirm water heater type matches plumbing plans | Checked (no comments)
| 2P | Confirm water heater efficiency is correct | N/A
| 3P | Confirm water heater location is correct | Checked (no comments)
| 4P | Confirm heater and tank count are correct | Checked (no comments)
5P
Electrical | 1E | Confirm light fixture wattages (if applicable) | Checked (no comments)
| 2E | Confirm fixture counts in spaces (if applicable) | Checked (no comments)
3E
4E
5E